## About (hidden)
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: TPMC New Website
Annex Developer |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riki M.
Project start date: | 2023-08-01 | 2023-08-24 |  |  |  | August | [34 empty] | September
Scrolling increment: | 0 | time axis 2023-08-01 to 2023-09-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-08-01 to 2023-09-25
WEB DESIGN GUI |  |  |  | 2023-08-01
Home Page | On Track | Name | 95% | 2023-08-08 | 7
Login Page | On Track |  | 90% | 2023-08-12 | 5
Admin Page | Milestone |  | 10% | 2023-08-05 | 15 | bar: 2023-08-05 to 2023-08-19
Vendor Page | On Track |  | 95% | 2023-08-13 | 8
Member Page | Med Risk |  | 10% | 2023-08-24 | 30
Non-Member Page | Med Risk |  | 5% | 2023-08-24 | 30
VENDOR
POS | On Track |  | 90% | 2023-08-14 | 5
Summary of Total sales | On Track |  | 90% | 2023-08-26 | 3
Summary of Total sales | On Track |  | 90% | 2023-08-28 | 8
Summary of Total sales | On Track |  | 90% | 2023-08-16 | 3
ADMIN
Member Profile | On Track |  | 100% | 2023-08-18 | 3
Member Share summary report
Account receivable
Payment summary
Chat room (for checking if needed) | Milestone |  | 100% | 2023-08-18 | 7 | bar: 2023-08-18 to 2023-08-24
PM ( for member and Admin) | Goal |  | 100% | 2023-08-18 | 7 | 2023-08-18: 2; 2023-08-19: 2; 2023-08-20: 2; 2023-08-21: 2; 2023-08-22: 2; 2023-08-23: 2; 2023-08-24: 2
Loans summary
Manage Loan (admit for editing)
Dividend
Account closure summary
Product à per Vendor account + Dummy Account for Bazaar | On Track |  | 100% | 2023-08-18 | 7
Coop e-learning
POS REPORT – one week transaction
POS Sales
Inventory – vendor & COOP
Cash in/out * -cash flow management
Loan Ledger (GPL) à*
Vendor Summary of Total sales – Need excel report for principal & COOP rebate per vendor code
Summary of list of purchased
Who’s online
Member
Online registration |  |  | 100%
Member & Non-member
Member Profile |  |  | 100%
Share History
Payments (with Option: G-cash or salary deduction)
Terms of Deduction
View Payment History
PM | Milestone |  | 100% | 2023-08-18 | 7 | bar: 2023-08-18 to 2023-08-24
Chat room (for checking if needed) | Goal |  | 100% | 2023-08-18 | 7 | 2023-08-18: 2; 2023-08-19: 2; 2023-08-20: 2; 2023-08-21: 2; 2023-08-22: 2; 2023-08-23: 2; 2023-08-24: 2
Cash Loans
Appliance loan
View my Dividend
Account closure
Product | On Track |  | 100% | 2023-08-18 | 10
Coop e-learning
User payment summary
Online ordering (add to cart) | On Track |  | 95% | 2023-08-19 | 8
Design
Feasibility study | On Track |  | 10% | 2023-08-23
Submit permit applications | Med Risk |  |  | 2023-08-26
Design proposal | On Track |  |  | 2023-09-10
Materials | Goal |  |  | 2023-09-09
Equipment | Low Risk |  |  | 2023-08-24
Testing
Environment |  |  |  | 2023-09-12
System test |  |  |  | 2023-09-26
Issues/bugs | Milestone |  |  | 2023-11-07
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark (hidden)
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2023-08-24 |  |  |  |  | August | [6 empty] | September | [27 empty] | October
Scrolling increment: | 5 | time axis 2023-08-29 to 2023-10-23
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2023-08-24 | 3
Task 2 | Milestone |  |  | 2023-08-29 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2023-08-21 | 10
Task 4 | Milestone |  |  | 2023-09-13 | 1 | bar: W
Task 5 | Med Risk |  | 10% | 2023-08-30 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-08-30 | 13
Task 2 | On Track |  | 50% | 2023-09-01 | 9
Task 3 | Low Risk |  | 33% | 2023-09-06 | 11
Task 4 | Milestone |  |  | 2023-09-08 | 1 | bar: F
Task 5 |  |  |  | 2023-09-09 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-09-08 | 4
Task 2 | Med Risk |  |  | 2023-09-11 | 14
Task 3 | On Track |  |  | 2023-09-26 | 6
Task 4 | Goal |  |  | 2023-09-30 | 3 | S: 2; S: 2; M: 2
Task 5 | Low Risk |  |  | 2023-08-30 | 19
TITLE 4
Task 1 |  |  |  | 2023-10-03 | 15
Task 2 |  |  |  | 2023-10-17 | 5
Task 3 | Milestone |  |  | 2023-11-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color (hidden)
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2023-08-24 |  |  |  |  | August | [6 empty] | September | [27 empty] | October
Scrolling increment: | 5 | time axis 2023-08-29 to 2023-10-23
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-08-29 to 2023-10-23
TITLE 1
Task 1 | Goal | Name | 25% | 2023-08-24 | 3
Task 2 | Milestone |  |  | 2023-08-29 | 1 | bar: 2023-08-29
Task 3 | Low Risk |  | 50% | 2023-08-21 | 10
Task 4 | Milestone |  |  | 2023-09-13 | 1 | bar: 2023-09-13
Task 5 | Med Risk |  | 10% | 2023-08-30 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-08-30 | 13
Task 2 | On Track |  | 50% | 2023-09-01 | 9
Task 3 | Low Risk |  | 33% | 2023-09-06 | 11
Task 4 | Milestone |  |  | 2023-09-08 | 1 | bar: 2023-09-08
Task 5 |  |  |  | 2023-09-09 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-09-08 | 4
Task 2 | Med Risk |  |  | 2023-09-11 | 14
Task 3 | On Track |  |  | 2023-09-26 | 6
Task 4 | Goal |  |  | 2023-09-30 | 3 | 2023-09-30: 2; 2023-10-01: 2; 2023-10-02: 2
Task 5 | Low Risk |  |  | 2023-08-30 | 19
TITLE 4
Task 1 |  |  |  | 2023-10-03 | 15
Task 2 |  |  |  | 2023-10-17 | 5
Task 3 | Milestone |  |  | 2023-11-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one